## Front End
Front End SoC Design |  |  | Task | Assigned To | Scheduled Completion |  | Current Status/Note | Reference/Link
Reported By | Greg Martin |  |  |  | original | current
Last Update | 2021-11-09 | 1 | Identify/procure the PLL source | Tim Saxe | 2021-05-01 | 2021-09-28 | Complete
|  | 2 | Design verification plan, including bare-metal for verification | Greg Martin | 2021-05-01 | TBD | no documentation of verification plan. Spreadsheet available, should be published in the repo (CORE-V MCU). Jasper and Greg working on the spreadsheet
| Design Completion | [5 empty] | take cv32e40p checklist as prototype - book meeting to review
|  | 3 | PLL connected | Greg Martin |  | 2021-09-28 | selected, working with CMC/GF to get data/specs; Greg now has datasheet to integrate; licensing terms TBD
|  | 4 | eFPGA test mode | Randy |  |  | resolved
|  | 5 | Resolve IO details such as POWEROK signal | Greg Martin |  | 2021-09-28 | complete; test transmission to CMC this week
|  | 6 | Triage error/warning messages | Greg Martin |  | 2021-09-29 | 95% complete
|  | 7 | SDC time constraints | Greg Martin |  | 2021-09-30 | done but needs to continue to be checked
|  | 8 | Resolve blackboxes such as register files | Greg Martin |  | 2021-09-30 | complete
|  | 9 | Run all verification test on post synthesis | Greg Martin;Randy;Somesh |  | 2021-09-24 | Done except PLL is pending
|  | 10 | Run all verification test on post P&R netlist | Greg Martin;Randy;Somesh |  | 2022-01-26 | Depends on backend PnR and GDS
|  | 11 | RTL handoff #1 with partial completion of RTL Freeze Checklist | Greg Martin |  | 11/15/2021 proposed to move to 11/30/2021 | Sftp access tested. CMC not planning to get fully started until mid November. But plan to get initial versions over to CMC by date on left
|  | 12 | bitstream for Genesys2 board complete | Greg Martin |  | TBD
|  | 13 | pinout check for eFPGA | Greg Martin |  | TBD
|  | 14 | open source eFPGA flow documented | Greg Martin |  | TBD
|  |  | Decision to include/remove FPU |  |  |  | Resolved: FPU is disabled
|  |  | Fix bug in debug unit identified by Jeremy; issue #159 |  |  |  | Davide, Greg, Jeremy to have live session to review logic traces
|  |  | BootROM | Greg Martin |  |  | Need to compile; plan B is boot from JTAG
|  |  | Generate RTL Freeze checklist | Mike Thompson
|  |  | RTL Freeze Milestone with full completion of Checklist (superset of E40P) | Greg Martin |  | proposed 12/30/2021

## Back End and Fabrication
Back End SoC Design |  |  | Task | Assigned To | Scheduled Completion |  | Current Status/Note | Reference/Link
Reported By | Hugh Pollitt-Smith |  |  |  | original | current
Last Update | 2021-09-29 | 0 | Initial (informal) place and route |  |  |  | to be scheduled
|  | 1 | Start place and route | CMC | 2021-07-01 | 2021-11-15
|  | 2 | Publish GDS Freeze checklist to Github | CMC | 2021-07-01 | 2021-11-15
|  | 3 | Complete place and route, GDS | CMC | 2021-09-01 | 2022-01-26 | Hugh to create/work with Foundry on checklists
|  | 4 | Complete Design submission (MPW2245, est. delivery date 2022-06-30) | CMC | 2021-09-01 | 2022-01-26
|  |  | Final submission date for MPW2245 | CMC |  | mid Feb | fill in the final deadline

## Chip Packaging
SoC Packaging |  |  | Task | Assigned To | Scheduled Completion |  | Current Status/Note | Reference/Link
Reported By | Anthony Le |  |  |  | original | current
Last Update | 2021-10-27
|  | 2 | Prepare packaging plan (low volume, ~50 I/Os, wire-bonding) and upload to Github | Anthony Le, Feng | 2021-05-01 | 2022-01-27 | depend on back end design completion
|  | 3 | Chip package design complete | CMC | 2022-04-01 | 2022-02-11 | Need to check
|  | 4 | Send Chips for package assembly (first devices) | CMC external contractor |  | 2022-06-01
|  | 5 | Packaged chips back (see Test PCB for date of delivery to Test PCB) |  |  | 2022-06-30

## Test PCB and MCU test
Test Board (AKA Bench board) |  |  | Task | Assigned To | Scheduled Completion |  | Current Status/Note | Reference/Link
Reported By | Anthony Le |  |  |  | original | current
|  | 1 | Prepare IC production test plan and upload to Github | Anthony Le, James Millar | 2021-05-01 | 2022-02-02 | None as yet
Last Update | 2021-11-10 | 2 | Upload Test PCB Specification to Github | Anthony Le (QL), James Millar (CMC) | 2021-05-01 | 2021-11-01 |  | Anthony will email spec around; preference to use ORCAD/Allegro but will look into how to export to use in an open-source tool (Kicad)
|  | 3 | PCB Design Complete | Anthony Le (QL), James Millar (CMC) | 2021-11-01 | 2022-02-25 | backend+15 days
|  | 4 | PCB manufacturing and assembly complete (without MCU) | Anthony Le (QL), James Millar (CMC) | 2022-04-01 | 2022-03-28 | Line 4 + 20 days
|  | 5 | Initial bringup of \ PCB (without MCU) testing complete | Anthony Le (QL), James Millar (CMC) | 2022-03-01 | 2022-03-31 | Line 5 + 3 days
|  | 6 | QL receives packaged MCU chips |  |  | 2022-06-30
|  | 7 | Characterization plan (plan to test operation of the first received board with chip) complete and upload to Github | Anthony Le (QL), James Millar (CMC) | 2022-05-01 | TBD | Line 6 + TBD
|  | 8 | PCB + MCU quick bringup test | Anthony Le (QL) |  | 2022-07-01
|  | 9 | PCB + MCU full characterization testing | Anthony Le (QL) |  | TBD
|  | 10 | CORE-V MCU DS (Datasheet) complete | Anthony Le (QL) |  | 2022-08-01 | Are there any examples of datasheets from OpenHW?

## - move to DEV-KIT project
Devkit PCB |  |  | Task | Assigned To | Scheduled Completion |  | Current Status/Note | Reference/Link
Reported By | Anthony Le |  |  |  | original | current
Last Update | 2021-10-04 | 1 | Upload PCB Specification to Github | Anthony Le, James Millar | 2021-05-01 | 2022-03-04 | Initial Devkit specification was presented in June at HW TG. Needs review with Hugh O'Keeffe | Link?
|  | 2 | PCB Design Complete | Anthony Le, James Millar | 2021-11-01 | 2022-03-11 | Who pays for the EVK?
|  | 3 | PCB manufacturing and assembly | Anthony Le, James Millar | 2022-04-01 | 2022-03-25
|  | 4 | Characterization plan (testing operation of the first received board and chip) complete and upload to Github | Anthony Le, James Millar | 2022-03-01 | 2022-04-28
|  | 5 | Initial bringup PCB testing complete | Anthony Le, James Millar | 2022-05-01 | 2022-05-03

## Test SW
Test SW Integration |  |  | Task | Assigned To | Scheduled Completion |  | Current Status/Note | Reference/Link
Reported By | Greg Martin |  |  |  | original | current
Last Update | 2021-09-22 | 1 | Structure prototype HAL as needed from PULP SDK |  | 2021-04-01 |  | done
|  | 2 | Initial FreeRTOS/HAL/MCU integration |  | 2021-04-01 |  | done
|  | 3 | Complete Starter project |  | 2021-04-01 |  | done
|  | 4 | Specify and complete FreeRTOS demo application (TensorFlow Lite); |  | 2021-06-01 |  | done
|  | 5 | Whole product test plan (the SW testing needed to complete the MCU project) | Greg Martin |  | TBD

## PA checklist
| PA Gate Criteria | Detail | MCU-SoC
PA Gate Preparation
Reported By | Jasper Lin, Hugh Pollitt=Smith, Duncan Bees
Last Update | 2021-10-25
Top Level Items for PA Gate
| Requirements Specification | V1 agreed by TWG - see below for breakdown | In progress - https://github.com/openhwgroup/core-v-mcu/blob/master/docs/doc-src/overview.md
| Project Plan | V1 agreed by TWG - see below for breakdown | This spreadsheet + "PA" document
Requirements Specification Item
| Document available on Github | V1 for review | https://docs.openhwgroup.org/projects/core-v-mcu/doc-src/overview.html
| Document format | Markdown (RST, AsciiDocs, MD, etc.). All high level features should be identified (e.g. "security extensions"), with at least another level of detail down (e.g. "protection for CSR") | RST + MD
Project Plan Item
Availability & Format
| Plan document | V1 for review on Github | This document, accompanied by Plan Approved (PA) MD file
| Plan Document format | Plan could be any (editable) format | Spreadsheet
| Set of artifacts | What artifacts (schedule charts, project boards, etc.) will be used for project planning | PA: spreadsheet containing tasks and planning dates for tasks.
| Plan artifacts available on Github | Initial version of project artifacts | yes - this document
| Note how planning artifacts and tools will be available to OpenHW members |  | plan docs: core-v-docs/program/Project Descriptions and Plans/CORE-V MCU SoC/
Note Any Changes from PL
| Summary |  | PA has been updated compared with PL - all sections updated.
| Components | Will be used to drive task list or backlog below | See PA doc
| Members committed to participate |  | See PA doc
| TPL/PM |  | See PA doc
| Project Documents |  | See PA doc
| Project Outputs |  | See PA doc
| Resources | Will lead into resource plan below | See PA doc
| Summary of Requirements |  | See PA doc
| Repository Structure |  | See PA doc
| Distribution Model |  | See PA doc
| Any other changes |  | See PA doc
See PA doc
Planning Approach
| Scope (e.g. design, design+verification, verification) | Are design and verification handled as a unified project or with separate projects? | Single project covering design, verification and whole product test
| Methodology (waterfall/agile/hybrid) |  | Waterfall
| Method for assigning tasks to persons | For Sprints or for waterfall assignment, do we consider design and verification as two different planning domains? | Single coordinated project coordinated by OpenHW staff, Jasper Lin and Hugh Pollitt-Smith
| Method for tracking tasks | How do OpenHW members see who is doing what? | this spreadsheet
| Planning tools disclosed (e.g. for schedule, project boards, Gantt charts) | Enough visibility on the tools to support collaborative multi-member development | this spreadsheet
Project Organization
| Project structure or hierarchy if applicable |  | Resources described in PA document
| Project meeting cadence and timeslot |  | weekly project sync up meeting on top of HW TG meeting
| Organization of interlocking projects | Different teams and plans for interlocked projects (e.g. cv32e40x and s) | MCU team handles MCU integration, with test SW as needed from SW group
| How design, verification, s/w, h/w teams interface | E.g., will there be separate or joint meetings for design and verification? | Led by MCU/HW TG team
Human Resources
| Person(s) responsible for project planning | presumably the TPL/PM identified in PL gate | Jasper Lin, Hugh Pollitt-Smith, coaching from Duncan Bees
| Person(s) responsible for checklist verification | That is, this is the person/persons who need to sign off on the checklists | See Dcoument and Checlist section
| Resource requirement breakdown for components/phases | To support multi-member development: Coarse grained view of project resource needs. For example, 2 design engineer months for design component x, 3 verification engineer months for verification component y | most detailed tasks have a name or company assigned
| Resource plan to meet requirements | Available people to allocate against resource needs | most detailed tasks have a name or company assigned
| Flag resource issues or risks |  | most detailed tasks have a name or company assigned
Material Resources
| Test boards, platforms or equipment |  | Test PCB board
| Specify the set of EDA tools required for a designer or verification person to be involved in the project. | E.g. verilog simulator, reference model license, etc. | standard core-v-verif testbench and standard design tools
| Specify the set of s/w tools needed for a resource to be involved |  | n/a
Risks and Dependencies
| Dependencies on external technology or efforts | E.g., external standard needs to be ratified | PLL source, see Front End
| Cross-project dependencies: related projects (e.g. s/w linked to a h/w project) | E.g., s/w or design task planned outside the project needs to be finished | This project is mainly feeding in to CORE-V SDK and Dev-kit
| Cross-project dependencies: linked projects | E.g. dependence on a task linked to a separate Cores project. | n/a
| Risk-register | Risks, impacts, and mitigation plan | see PA document
Schedule
| V1 of planned schedule | uploaded on Github | Spreadsheet view is being used
| Delineate coarse grained timeline | Project can organize the timeline according to the project nature, but schedule could be tied to major chunks of functionality. E.g. complete design for major component by end Q2 2022, etc. | See PA doc
| Milestones | Possibly tied to components, at least 2-3 would be ideal | See this spreadsheet
| Project Freeze planning date |  | August or September 2022
Waterfall Specific Items
| Task breakdown | E.g. tasks could be viewed as 1 week duration. Detail at front end expected to be higher | Available (this document)
| Gantt Chart, or another way of scheduling tasks and resource assignments | Detail at front end expected to be higher | as per above, task breakdown
Agile Specific Items
| Agile Methodology | Scrum, Kanban, other | n/a
| What element does the project backlog track | Features, tasks, or other | n/a
| Project backlog structure | How is it captured and maintained | n/a
| Initial project backlog | Nature of backlog items to be specified (features, tasks) | n/a
| Sprint Backlog | if used, how is it built | n/a
| Kanban/ project board | if used, how is it built, and how are tasks allocated | n/a
| Sprint Planning method | how is each Sprint planned (e.g. Sprint planning meeting, decided by a TPL, etc.). How do OpenHW contributors get involved | n/a
| Daily Standup Meeting | if used, how is it organized | n/a
| Sprint Review Meeting | if used, how is it organized | n/a
| Sprint Retrospective Meeting | if used, how is it organized | n/a
| How are "done" tasks updated on Github |  | n/a
| How are these artifacts made available on Github |  | n/a
| Initial Gantt type schedule (like in Waterfall) | Optional to have an initial view of the project. Took approx 1 week of effort of leaders in cv32e40p | n/a
Issue Management
| Overall approach for Github issues and labels |  | https://github.com/openhwgroup/core-v-mcu/issues
| Task planning | template if available | tbd
| Bugs | template if available | tbd
| Checklist review | template if available | tbd
IP Issues
| Anticipated Contribution Questionnaire |  | CQ was done in August 2021, status = checked in
| Any deviation from project license approach from PL gate |  | n/a
| LIcense.md file | should exist | https://github.com/openhwgroup/core-v-mcu/blob/master/LICENSE.md
Project Freeze Criteria
| Describe approach to checklists | likely as per cv32e40p | see Documentation and Checklists tab
| Project Release version approach | likely as per cv32e40p | Release number to take into account FPGA emulation and SoC
| Project Release estimated schedule | taking into account Eclipse release process | First FPGA release Feb 2022

## Docmntn & Checklists
|  |  | Task | Assigned To | Scheduled Completion |  | Current Status/Note | Reference/Link
Reported By | Duncan Bees |  |  |  | original | current
Last Update | 2021-10-26 | 1 | PA project document | Duncan;Hugh;Jasper |  | 2021-10-01 | Done
|  | 2 | Project plan spreadsheet | Duncan;Hugh;Jasper |  | 2021-10-01 | Done
|  | 3 | MCU User Manual (ReadTheDocs) | QuickLogic |  | 2022-02-17 | Depends on backend design
|  | 4 | Datasheet include operating conditions, AC/DC parameters, basic timing information | Tuan |  | 2022-08-01 | Depends on bench PCB design
|  | 5 | Test PCB Specification | Anthony |  | 2021-11-01
|  | 6 | Whole Product Test spec (SoC/s/w testing - preRTOS, FreeRTOS) | Anthony;Greg |  | TBD | Take another look
|  | 7 | Verification plan | Greg |  | TBD | Excel version of the verif plan exists, Greg to point to it
|  | 8 | Device Characterization plan | Anthony |  | TBD
|  | 9 | FPGA user guide/setup | Greg, Hugh |  | TBD
|  | 10 | Chip package design | CMC |  | 2022-02-11
CHECKLISTS FOR PROJECT FREEZE
|  |  | IP checklist | Duncan, Greg |  | 2021-11-01
|  |  | RTL Freeze checlist | Mike, Greg |  | end of 2021
|  |  | Verification checklist | Mike, Greg |  | 2021-11-01 | Nov 2021 view: yes we need to complement the verif plan
|  |  | ASIC implementation - synthesis | Greg, Hugh |  | 2022-08-01
|  |  | ASIC implementatoin - test results | Greg, Anthony |  | 2022-08-01
|  |  | Manufacturing checklist | Hugh, Anthony |  | 2022-08-01

## Task-Resource (obsolete)
Category | Task List | Assigned to | Assigned to Sep view | Sept View. | Sep Comment | April view: to be completed in | Estimated duration | % complete
Last Update
Documentation and Gate Review | Update PL document | Hugh, Tim, Duncan |  | Done |  | April | 1 day | done
| Complete Project plan document/spreadsheet | Hugh, Tim, Duncan |  | Sep |  | April |  | done
| SoC specification/user manual | Tim | Greg | Sep | Autogenerated rendered on RTD. Editing needed | April | 5d | in progress
| Datasheet include operating conditions, AC/DC parameters, basic timing information |  | Hugh | Oct (initial) |  | September |  | not started
| "Whole Product Test" spec (SoC/s/w testing - preRTOS, FreeRTOS) | Tim |  |  | Strategy developed but needs documentation. reach out to Richard Berry for assistance. Get FreeRTOS integration on MCU on SW TG meeting for next call. Robert/Shteryana may have issues but may not have been raised. | May | 5d | 50%
| Evaluation kit (SDK, overall Devkit, out of box experience, wiki) specification/user guide | Anthony, James |  | no change | Hugh O'Keeffe has a lot to say about this and can help drive this | May (2022)
| Evaluation kit examples/demos | Anthony, James |  | no change | " | May (2022)
Project Setup
| Merge Quicklogic/OpenHW Repo | Tim, Florian, Greg |  | done | has happened | April |  | done
| Repo review, license review for CQ | Duncan, Florian |  | Sep | CQ is starting | May
SoC Design
Front End Design
| Identify/procure the PLL source | Tim, Rick |  |  | PLL was resolved. Tim to confirm | May
| Design verification plan, including bare-metal for verification | Tim |  |  | no documentation of verification plan. Spreadsheet available, should be published in the repo (CORE-V MCU) | May | 5d
| RTL Freeze checklist | QuickLogic |  |  | take cv32e40p checklist as prototype - book meeting to review | May | 2d
| RTL Freeze/Golden RTL | QuickLogic |  |  | need update from Tim | May | 20d
| Begin synthesis | QuickLogic |  |  | " | May | 30d
| Complete synthesis/Golden netlist | Quicklogic |  |  | " | July
BackEnd design
| Start place and route | CMC |  |  |  | July | 1d
| GDS Freeze checklist | CMC |  |  | Hugh to create/work with Foundry on checklists | July | 5d
| Complete place and route, GDS | CMC |  |  |  | September | 60d
| Design submission (MPW2243, est. delivery date 2022-03-31) | CMC |  |  |  | September | 1d
SoC Packaging and Test
| Production test plan (IC) | Anthony, James |  |  | Hugh to investigate status | May
| Packaging plan - low volume, ~50 I/Os, wire-bonding | Anthony, CMC, Florian |  |  |  | May
| Chip packaging | TBD |  |  |  | April (2022)
| Chip/packaging test | Anthony, James |  |  |  | April (2022)
PCB Design and Manufacture
| PCB Specification | Anthony, James |  |  | Initial specification was presented in June at HW TG. Needs review with Hugh O'Keeffe | May
| PCB Design | Anthony, James |  |  |  | November
| PCB manufacturing and assembly | Anthony, James |  |  |  | April (2022)
| Characterization plan (testing operation of the first received board and chip)_ | Anthony, James |  |  |  | March (2022)
| Initial bringup PCB testing | Anthony, James |  |  |  | May (2022)
Software Integration
Prototype FreeRTOS/MCU integration
| Structure prototype HAL as needed from PULP SDK | Greg |  |  |  | April |  | done
| FreeRTOS/HAL/MCU integration (initial) | Greg |  |  |  | April |  | done
| Starter project (blinky) | Greg |  |  |  | April | 2d
| FreeRTOS demo application (TensorFlow Lite); | Greg |  |  |  | June
FreeRTOS merge
| Merge FreeRTOS into OpenHW master | Greg, Robert, Shteryana |  |  |  | to be scheduled
OpenHW HAL creation
| Project Concept | Yunhai |  |  |  | May
| Project Launch | Yunhai |  |  |  | June
| Project Freeze | Yunhai
Eval kit s/w integration
| Release current FPGA emulation (available only as build) | Florian |  |  |  | May
| FreeRTOS, HAL, MCU Integration test |  |  |  |  | define checkpoints based on S/W considerations - to be scheduled