## Task-Resource Breakdown
Category | Task List | Assigned to | to be completed in | Estimated duration | % complete
Last Update
Documentation and Gate Review | Update PL document | Hugh, Tim, Duncan | April | 1 day | done
| Complete Project plan document/spreadsheet | Hugh, Tim, Duncan | April |  | done
| SoC specification/user manual | Tim | April | 5d | in progress
| Datasheet include operating conditions, AC/DC parameters, basic timing information |  | September |  | not started
| "Whole Product Test" spec (SoC/s/w testing - preRTOS, FreeRTOS) | Tim | May | 5d | 50%
| Evaluation kit specification/user guide | Anthony, James | May (2022)
| Evaluation kit examples/demos | Anthony, James | May (2022)
| Characterization plan (testing operation of the first received board and chip)_ | Anthony, James | March (2022)
Project Setup
| Merge Quicklogic/OpenHW Repo | Tim, Florian, Greg | April |  | done
| Repo review, license review for CQ | Duncan, Florian | May
SoC Design
Front End Design
| Identify/procure the PLL source | Tim, Rick | May
| Design verification plan, including bare-metal for verification | Tim | May | 5d
| RTL Freeze checklist | QuickLogic | May | 2d
| RTL Freeze/Golden RTL | QuickLogic | May | 20d
| Begin synthesis | QuickLogic | May | 30d
| Complete synthesis/Golden netlist | Quicklogic | July
BackEnd design
| Start place and route | CMC | July | 1d
| GDS Freeze checklist | CMC | July | 5d
| Complete place and route, GDS | CMC | September | 60d
| Design submission (MPW2243, est. delivery date 2022-03-31) | CMC | September | 1d
SoC Packaging and Test
| Production test plan (IC) | Anthony, James | May
| Packaging plan - low volume, ~50 I/Os, wire-bonding | Anthony, CMC, Florian | May
| Chip packaging | TBD | April (2022)
| Chip/packaging test | Anthony, James | April (2022)
PCB Design and Manufacture
| PCB Specification | Anthony, James | May
| PCB Design | Anthony, James | November
| PCB manufacturing and assembly | Anthony, James | April (2022)
| Initial bringup PCB testing | Anthony, James | May (2022)
Software Integration
Prototype FreeRTOS/MCU integration
| Structure prototype HAL as needed from PULP SDK | Greg | April |  | done
| FreeRTOS/HAL/MCU integration (initial) | Greg | April |  | done
| Starter project (blinky) | Greg | April | 2d
| FreeRTOS demo application (TensorFlow Lite); | Greg | June
FreeRTOS merge
| Merge FreeRTOS into OpenHW master | Greg, Robert, Shteryana | to be scheduled
OpenHW HAL creation
| Project Concept | Yunhai | May
| Project Launch | Yunhai | June
| Project Freeze | Yunhai
Eval kit s/w integration
| Release current FPGA emulation (available only as build) | Florian | May
| FreeRTOS, HAL, MCU Integration test |  | define checkpoints based on S/W considerations - to be scheduled

## PA checklist
| PA Gate Criteria | Detail | MCU-SoC
Last update | 2021-04-26
Top Level Items for PA Gate
| Requirements Specification | V1 agreed by TWG - see below for breakdown | In progress - https://github.com/openhwgroup/core-v-mcu/blob/master/docs/doc-src/overview.md
| Project Plan | V1 agreed by TWG - see below for breakdown | This document - (i) PA checklist. (ii) Schedule (iii) Risks
Requirements Specification Item
| Document available on Github | V1 for review | https://docs.openhwgroup.org/projects/core-v-mcu/doc-src/overview.html
| Document format | Markdown (RST, AsciiDocs, MD, etc.). All high level features should be identified (e.g. "security extensions"), with at least another level of detail down (e.g. "protection for CSR") | RST + MD
Project Plan Item
Availability & Format
| Plan document | V1 for review on Github | This document, accompanied by Project Launch (PL)
| Plan Document format | Plan could be any (editable) format | Spreadsheet
| Set of artifacts | What artifacts (schedule charts, project boards, etc.) will be used for project planning | PA: spreadsheet containing tasks and planning dates for tasks. Gantt chart in preparation
| Plan artifacts available on Github | Initial version of project artifacts | yes - this document
| Note how planning artifacts and tools will be available to OpenHW members |  | plan docs: core-v-docs/program/Project Descriptions and Plans/CORE-V MCU SoC/
Note Any Changes from PL
| Summary |  | PL has been updated compared with PPL - all sections updated.
| Components | Will be used to drive task list or backlog below | see PL doc
| Members committed to participate |  | see PL doc
| TPL/PM |  | see PL doc
| Project Documents |  | see PL doc
| Project Outputs |  | see PL doc
| Resources | Will lead into resource plan below | see PL doc
| Summary of Requirements |  | see PL doc
| Repository Structure |  | see PL doc
| Distribution Model |  | see PL doc
| Any other changes |  | see PL doc
see PL doc
Planning Approach
| Scope (e.g. design, design+verification, verification) | Are design and verification handled as a unified project or with separate projects? | Single project
| Methodology (waterfall/agile/hybrid) |  | Waterfall due to nature of IC fabrication and diverse tasks
| Method for assigning tasks to persons | For Sprints or for waterfall assignment, do we consider design and verification as two different planning domains? | Single coordinated project coordinated by Tim Saxe and Hugh Pollitt-Smith
| Method for tracking tasks | How do OpenHW members see who is doing what? | this document
| Planning tools disclosed (e.g. for schedule, project boards, Gantt charts) | Enough visibility on the tools to support collaborative multi-member development | this document
Project Organization
| Project structure or hierarchy if applicable |  | Resources described in PL document
| Project meeting cadence and timeslot |  | biweekly meeting on top of HW TG meeting
| Organization of interlocking projects | Different teams and plans for interlocked projects (e.g. cv32e40x and s) | MCU team handles MCU integration, with feed-in from S/W groups
| How design, verification, s/w, h/w teams interface | E.g., will there be separate or joint meetings for design and verification? | Led by MCU/HW TG team
Human Resources
| Person(s) responsible for project planning | presumably the TPL/PM identified in PL gate | Tim Saxe, Hugh Pollitt-Smith, Duncan Bees
| Person(s) responsible for checklist verification | That is, this is the person/persons who need to sign off on the checklists | TBD
| Resource requirement breakdown for components/phases | To support multi-member development: Coarse grained view of project resource needs. For example, 2 design engineer months for design component x, 3 verification engineer months for verification component y | in progress
| Resource plan to meet requirements | Available people to allocate against resource needs | in progress
| Flag resource issues or risks |  | in progress
Material Resources
| Test boards, platforms or equipment |  | Eval Kit manufacturing plan in progress
| Specify the set of EDA tools required for a designer or verification person to be involved in the project. | E.g. verilog simulator, reference model license, etc. | in progress
| Specify the set of s/w tools needed for a resource to be involved |  | in progress
Risks and Dependencies
| Dependencies on external technology or efforts | E.g., external standard needs to be ratified | in progress
| Cross-project dependencies: related projects (e.g. s/w linked to a h/w project) | E.g., s/w or design task planned outside the project needs to be finished | in progress
| Cross-project dependencies: linked projects | E.g. dependence on a task linked to a separate Cores project. | in progress
| Risk-register | Risks, impacts, and mitigation plan | in progress
Schedule
| V1 of planned schedule | uploaded on Github | Task list and schedule completion completed, Gantt view in progress
| Delineate coarse grained timeline | Project can organize the timeline according to the project nature, but schedule could be tied to major chunks of functionality. E.g. complete design for major component by end Q2 2022, etc. | "
| Milestones | Possibly tied to components, at least 2-3 would be ideal | :
| Project Freeze planning date |  | Approx May 2022 - detailed plan in progress
Waterfall Specific Items
| Task breakdown | E.g. tasks could be viewed as 1 week duration. Detail at front end expected to be higher | Available (this document)
| Gantt Chart, or another way of scheduling tasks and resource assignments | Detail at front end expected to be higher | in progress
Agile Specific Items
| Agile Methodology | Scrum, Kanban, other | n/a
| What element does the project backlog track | Features, tasks, or other | n/a
| Project backlog structure | How is it captured and maintained | n/a
| Initial project backlog | Nature of backlog items to be specified (features, tasks) | n/a
| Sprint Backlog | if used, how is it built | n/a
| Kanban/ project board | if used, how is it built, and how are tasks allocated | n/a
| Sprint Planning method | how is each Sprint planned (e.g. Sprint planning meeting, decided by a TPL, etc.). How do OpenHW contributors get involved | n/a
| Daily Standup Meeting | if used, how is it organized | n/a
| Sprint Review Meeting | if used, how is it organized | n/a
| Sprint Retrospective Meeting | if used, how is it organized | n/a
| How are "done" tasks updated on Github |  | n/a
| How are these artifacts made available on Github |  | n/a
| Initial Gantt type schedule (like in Waterfall) | Optional to have an initial view of the project. Took approx 1 week of effort of leaders in cv32e40p | n/a
Issue Management
Overall approach for Github issues and labels
| Task planning | template if available | tbd
| Bugs | template if available | tbd
| Checklist review | template if available | tbd
IP Issues
| Anticipated Contribution Questionnaire |  | May, 2021
| Any deviation from project license approach from PL gate |  | n/a
| LIcense.md file | should exist | https://github.com/openhwgroup/core-v-mcu/blob/master/LICENSE.md
Project Freeze Criteria
| Describe approach to checklists | likely as per cv32e40p | MCU checklist to be developed
| Project Release version approach | likely as per cv32e40p | to be developed
| Project Release estimated schedule | taking into account Eclipse release process | to be developed