## Slide 1: CV32E40Pv2 Project Launch (PL gate)
Pascal Gouedo, Dolphin Design
Technical WG, 2021-11-22

## Slide 2: Introduction
Project Concept approved on 2021-07-05
  core-v-docs/Project_Concept_for_CV32E40Pv2_June 2028.md
Summary of the Project:
  This project is about verifying PULP basic instructions disabled during CV32E40Pv1 phase. The goal of these instructions is to improve performance, power consumption and even code size depending on application programs.

## Slide 3: Component 1 - RTL
Starting from CV32E40P RTL freeze (cv32e40p_v1.0.0 release)
Re-encode all PULP instructions in custom-0 to 3 extensions (today disseminated in standard extensions) and Verify them
    Post-increment and register-register indexed load/store
    Hardware loops
    General ALU extensions
    Immediate branch
    Multiply-accumulate
    Bit manipulation
    SIMD (16 and 8-bit data)
    Event load

## Slide 4: Component 1 - RTL
Single Precision Floating Point support
  Keep Floating Point instructions decoding inside the Core and Dispatch their execution to APU interface
  Use ETHZ FPnew as FP execution unit (or FPnew moved to CV-FPU OpenHW Group project?)
  Verify RISC-V standard F extension instructions with coupled Core-FPnew (in both Zfinx and non-Zfinx modes?)
  Keep it optional with a parameter
Verify PULP Zfinx
  Keep it optional (?) to be able to use standard SW toolchain
Verified configurations
  PULP_XPULP = 1, PULP_CLUSTER = 1, FPU = 0
  PULP_XPULP = 1, PULP_CLUSTER = 1, FPU = 1, PULP_ZFINX = 0 (?)
  PULP_XPULP = 1, PULP_CLUSTER = 1, FPU = 1, PULP_ZFINX = 1

## Slide 5: Component 2 - Documentation
User Manual
  New encoding for all PULP instructions
  Re-factored FPU chapter with information imported from FPnew documentation
  Integration chapter with additional section about Core + FPnew wrapping
Verification architecture and reports
  Based on core-v-verif environment with UVM step and compare plus additional PULP instructions support in
    Imperas ISS
    SW toolchain
    Google RISC-V DV
  Plan and Reports
Implementation reports
  PPA analysis on different technologies and use cases (e.g. low area or high frequency)

## Slide 6: Tasks and Resources
Task list and estimated workload are in CV32E40pv2 task list
Dolphin Design
  Pascal Gouedo (architecture)
  Yoann Pruvost (design)
  ????? (design)
  Yoann Pruvost (verification lead)
  ????? (verification)
  ????? (verification)
OpenHW staff
  Davide
    Technical support (and more?)
  Mike
    Lead verification environment specification
    Verification technical support
Other members?

## Slide 7: External dependencies
SW toolchain including
  Re-encoded PULP instructions
  PULP Zfinx support
  Floating Point support
Imperas ISS
  Same features than SW toolchain
 Business negociation to finalize

## Slide 8: Timeline and Plan
Timeline
  Whole project is estimated between 14 and 20 person-months
    CV32E40pv2 task list
Plan
  PA – Plan approved – a fully detailed project plan and an agreed requirements specification as component of the User Manual
  End of Q4 2021
  PF – Project Freeze – Code released, all project checklists completed , and project completed
  With project starting in January 2022, RTL freeze would be end of Q2 2022

## Slide 9: Coordination
Planning tools will be setup using OpenHW Group recommendations and best practices (gantt chart using free ganttproject software?, spreadsheet ...).
CV32E40Pv2 meetings every week
  Cross-TG: Cores, Verification, SW
  Participants:
    Project contributors, including involved OpenHW staff
    OpenHW chairs and members welcome
Dedicated technical meetings when needed
Reporting to task groups and TWG (short)

## Slide 10
Thank you!