## Sheet1
| PA Gate Criteria | Detail (initial OpenHW remarks) | CV32E40S and X plan (input from Arjan Bink)
Top Level Items for PA Gate
| Requirements Specification | V1 agreed by TWG - see below for breakdown | The requirement specification for the CV32E40X and CV32E40S are provide by means of the User Manuals for these cores: https://cv32e40x.readthedocs.io/en/latest/ https://cv32e40s.readthedocs.io/en/latest/ The requirements correspond to the high level features which are documented in: https://cv32e40x.readthedocs.io/en/latest/intro/#standards-compliance https://cv32e40s.readthedocs.io/en/latest/intro/#standards-compliance https://cv32e40x.readthedocs.io/en/latest/integration/ https://cv32e40s.readthedocs.io/en/latest/integration/ This corresponds to the feature lists from: https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X/CV32E40X-PPL.md https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40S/CV32E40S-PPL.md
| Project Plan | V1 agreed by TWG - see below for breakdown | The CV32E40X and CV32E40S are being run as Agile projects. Priorities and tasks to be worked on are decided during the sprint planning meetings. There is no detailed up front project plan, but the major phases of the CV32E40X and CV32E40S projects (including the main features per phase) can be found in: https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X_CV32E40S_project_plan.pdf https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X_CV32E40S_project_plan.pdf
Requirements Specification Item
| Document available on Github | V1 for review | The requirement specification for the CV32E40X and CV32E40S are provide by means of the User Manuals for these cores: https://cv32e40x.readthedocs.io/en/latest/ https://cv32e40s.readthedocs.io/en/latest/ The requirements correspond to the high level features which are documented in: https://cv32e40x.readthedocs.io/en/latest/intro/#standards-compliance https://cv32e40s.readthedocs.io/en/latest/intro/#standards-compliance https://cv32e40x.readthedocs.io/en/latest/integration/ https://cv32e40s.readthedocs.io/en/latest/integration/ This corresponds to the feature lists from: https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X/CV32E40X-PPL.md https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40S/CV32E40S-PPL.md
| Document format | Markdown (RST, AsciiDocs, MD, etc.). All high level features should be identified (e.g. "security extensions"), with at least another level of detail down (e.g. "protection for CSR") | User Manual in RST format: https://cv32e40x.readthedocs.io/en/latest/ https://cv32e40s.readthedocs.io/en/latest/
Project Plan Item
Availability & Format
| Plan document | V1 for review on Github | This spreadsheet serves as the Plan document.
| Plan Document format | Plan could be any (editable) format, i.e. not PDF | This spreadsheet serves as the Plan document.
| Set of artifacts | What artifacts (schedule charts, project boards, etc.) will be used for project planning | The CV32E40X and CV32E40S are being run as Agile projects. Day to day tracking is performed via daily scrum meetings for active contributors based on a project back log (not publicly available on github). The major phases of the CV32E40X and CV32E40S projects (including the main features per phase) can be found in: https://github.com/openhwgroup/core-v-docs/blob/master/program/CV32E40X_CV32E40S_project_plan.pdf. Tasks involving alignment between multiple OpenHW contributors (e.g. contributors who are not involved on a day-to-day basis), as well as a subset of the larger tasks, are made visible via the following OpenHW github project boards: CV32E40X Design - https://github.com/openhwgroup/cv32e40x/projects/1 CV32E40S Design - https://github.com/openhwgroup/cv32e40s/projects/1 CV32E40X Testbench - https://github.com/openhwgroup/core-v-verif/projects/11 CV32E40S Testbench - https://github.com/openhwgroup/core-v-verif/projects/10 Core-V-Verif Common Infrastructure - https://github.com/openhwgroup/core-v-verif/projects/9 Known issues are tracked via: https://github.com/openhwgroup/cv32e40x/issues https://github.com/openhwgroup/cv32e40s/issues https://github.com/openhwgroup/core-v-verif/issues (with appropriate labels)
| Plan artifacts available on Github | Initial version of project artifacts | The major phases of the CV32E40X and CV32E40S projects: https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X_CV32E40S_project_plan.pdf https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X_CV32E40S_project_plan.pdf OpenHW github project boards: CV32E40X Design - https://github.com/openhwgroup/cv32e40x/projects/1 CV32E40S Design - https://github.com/openhwgroup/cv32e40s/projects/1 CV32E40X Testbench - https://github.com/openhwgroup/core-v-verif/projects/11 CV32E40S Testbench - https://github.com/openhwgroup/core-v-verif/projects/10 Core-V-Verif Common Infrastructure - https://github.com/openhwgroup/core-v-verif/projects/9 Known issues are tracked via: https://github.com/openhwgroup/cv32e40x/issues https://github.com/openhwgroup/cv32e40s/issues https://github.com/openhwgroup/core-v-verif/issues
| Note how planning artifacts and tools will be available to OpenHW members | OpenHW members will need to access current schedule and backlogs on Github | Tasks that require alignment between multiple OpenHW member will be made available on the stated OpenHW github project boards in a timely manner. Issues will reported as github issues.
Note Any Changes from PL
| Summary |  | For the CV32E40X there are no changes compared to https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X/CV32E40X-PPL.md. For the CV32E40S we intend to complete the majority of the design according to the original plan at https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40S/CV32E40S-PPL.md. However, design and verification of the Zce extension has on purpose been delayed to Q2 2022 to allow for some schedule tolerance if Zce is not ratified within 2021 as is the current RISC-V International target. The target is now more realistic with respect to the speed/progress of the RISC-V International ratification process. The real impact of this change is expected to be minimal as compiler support for Zce is likely not available by end of 2021 either.
| Components | Will be used to drive task list or backlog below
Members committed to participate
TPL/PM
Project Documents
Project Outputs
| Resources | Will lead into resource plan below
Summary of Requirements
Repository Structure
Distribution Model
Any other changes
Planning Approach
| Scope (e.g. design, design+verification, verification) | Are design and verification handled as a unified project or with separate projects? | CV32E40S: Design, verification, documentation (all similar to CV32E40P) CV32E40X: Design, verification, documentation (all similar to CV32E40P)
| Methodology (waterfall/agile/hybrid) |  | Agile (3-week long sprints)
| Method for assigning tasks to persons | For Sprints or for waterfall assignment, do we consider design and verification as two different planning domains? | Desig and verification are separate teams, but all members are present in the sprint planning sessions.
| Method for tracking tasks | How do OpenHW members see who is doing what? | Tasks that require alignment between multiple OpenHW members are made public via OpenHW github project boards. Other tasks are tracked internal to Silicon Labs via sprint reviews and a back log in Jira. Status of the CV32E40X and CV32E40S will be communicated regularly via Cores TG and Verification TG meetings.
| Planning tools disclosed (e.g. for schedule, project boards, Gantt charts) | Enough visibility on the tools to support collaborative multi-member development | Projects boards have been set up for tasks that require multi-member alignment as well as for certain relatively large tasks.
Project Organization
| Project structure or hierarchy if applicable |  | CV32E40X and CV32E40S are separate projects, but they share a common baseline derived from the CV32E40P. The Silicon Labs team of active contributors is shared between the two projects. The major phases in https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X_CV32E40S_project_plan.pdf, https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X_CV32E40S_project_plan.pdf show when people shift between projects.
| Project meeting cadence and timeslot |  | Status of the CV32E40X and CV32E40S designs will be presented at the (regular) OpenHW Cores TG meeting. Status of the CV32E40X and CV32E40S verification will be presented at the (regular) OpenHW Verification TG meeting.
| Organization of interlocking projects | Different teams and plans for interlocked projects (e.g. cv32e40x and s) | Within Silicon Laboratories both projects are tracked in the same Jira project board. In OpenHW various 2 github project boards have been set up for Design and 3 github project boards have been set up for Verification. Issues will be tracked as github issues (separate issue lists for CV32E40X and CV32E40S on the Design side; shared issue list on the Verification side).
| How design, verification, s/w, h/w teams interface | E.g., will there be separate or joint meetings for design and verification? | Interaction within Silicon Laboratories is done via (combined) daily scrum meetings. Multi-member interaction will be organized in an ad-hoc manner.
Human Resources
| Person(s) responsible for project planning | presumably the TPL/PM identified in PL gate | TPL (Øystein Knauserud) + PM (Øivind Ekelund)
| Person(s) responsible for checklist verification | That is, this is the person/persons who need to sign off on the checklists | TPL (Øystein Knauserud) + PM (Øivind Ekelund) + Arjan Bink + Steve Richmond
| Resource requirement breakdown for components/phases | To support multi-member development: Coarse grained view of project resource needs. For example, 2 design engineer months for design component x, 3 verification engineer months for verification component y | Will not be provided (as considered Silicon Laboratories internal details)
| Resource plan to meet requirements | Available people to allocate against resource needs | Silicon Laboraties is the major provider of resources (with 8 people involved). More detailed resource planning is considered internal business to Silicon Laboratories, Embecosm, Imperas, University of Bologna and ETH Zurich.
| Flag resource issues or risks |  | None identified
Material Resources
| Test boards, platforms or equipment |  | No test boards, chips, FPGA mappings are planned inside OpenHW context.
| Specify the set of EDA tools required for a designer or verification person to be involved in the project. | E.g. verilog simulator, Imperas reference model license, etc. | Apart from Silicon Laboratories the major expected contributions on the verification side are expected to come from Imperas and OneSpin. Imperas has committed to the CV32E40X and CV32E40S projects. OneSpin is not on board at this point in time and this is seen as a risk (needs to be resolved or worked around).
| Specify the set of s/w tools needed for a resource to be involved |  | Same as for CV32E40P.
Risks and Dependencies
| Dependencies on external technology or efforts | E.g., external standard needs to be ratified | The external dependencies mostly relate to not-yet-ratified specifications from RISC-V International and are described in: https://github.com/openhwgroup/core-v-docs/blob/master/program/CV32E40X-PPL.md https://github.com/openhwgroup/core-v-docs/blob/master/program/CV32E40S-PPL.md
| Cross-project dependencies: related projects (e.g. s/w linked to a h/w project) | E.g., s/w or design task planned outside the project needs to be finished | Alignment between OpenHW contributors (e.g. between Silicon laboratories and Embecosm and Imperas) will be done via the described OpenHW github project board as opposed to via the Silicon Laboratories internal Sprint process (which is in internal Jira). Alignment tasks will will pop up on the project boards at the appropriate times in the projects.
| Cross-project dependencies: linked projects | E.g. dependence on a task linked to a separate Cores project. | The CV32E40X and CV32E40S projects are linked to each other (see PL documents). There are currently no other dependent projects, although it is understood that not yet ratified RISC-V extensions as P, B, Zce are not supported by the compiler. An OpenHW software project aimed at support for Zce is encouraged, but is not part of the CV32E40X and CV32E40S projects themselves.
| Risk-register | Risks, impacts, and mitigation plan | With respect to the not yet ratified RISC-V extensions (ePMP, P, B, Zce) choices will be made roughly a quarter before the currently projected project end dates. Likely the desgin and verification at that point in time will be according to some non ratified specifications. If an extension is unratified we will make the call to either deconfigure such extension and delay support for it or sign off on a non ratified version (and allow for upgrade later). The allowed impact on the definition of RTL freeze and possible impact on the definition of the high level project phases will be discussed/clarified in the same time frame.
Schedule
| V1 of planned schedule | uploaded on Github | The schedule for the major phases of the CV32E40X and CV32E40S projects are shown in: https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X_CV32E40S_project_plan.pdf https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X_CV32E40S_project_plan.pdf
| Delineate coarse grained timeline | Project can organize the timeline according to the project nature, but schedule could be tied to major chunks of functionality. E.g. complete design for major component by end Q2 2022, etc. | See: https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X_CV32E40S_project_plan.pdf https://github.com/openhwgroup/core-v-docs/blob/master/program/Project%20Descriptions%20and%20Plans/CV32E40X_CV32E40S_project_plan.pdf This plan provides enough details to roughly know when alignment between OpenHW members is needed (e.g. to align on ISS support for the B extension). Further alignment will be done through OpenHW github project boards and ad-hoc meetings.
| Milestones | Possibly tied to components, at least 2-3 would be ideal | Each of the 3 phases of the CV32E40X project and each of the 2 phases of the CV32E40S project has 'design feature complete' and 'verification complete' milestones (with 'verification complete' being at the end of the shown phases and 'design feature complete' about a month before that. Both projects have their own 'RTL freeze' milestone.
| Project Freeze planning date |  | CV32E40S is targeted for completion in Q2 2022. CV32E40X is targeted for completion in Q4 2022.
Waterfall Specific Items
| Task breakdown | E.g. tasks could be viewed as 1 week duration. Detail at front end expected to be higher | n/a
| Gantt Chart, or another way of scheduling tasks and resource assignments | Detail at front end expected to be higher | n/a
Agile Specific Items
| Agile Methodology | Scrum, Kanban, other | Internal to Silicon Laboratories the projects are run with Scrums with a 3 week cadence.
| What element does the project backlog track | Features, tasks, or other | The project backlog tracks features (e.g. 'support bus errors'). Features are broken down into smaller tasks if needed. The backlog is maintained in (Silicon Laboratories internal) Jira. A single backlog is used for both the CV32E40X and CV32E40S project (as there are many shared tasks).
| Project backlog structure | How is it captured and maintained | Jira
| Initial project backlog | Nature of backlog items to be specified (features, tasks) | The initial project backlog is based on the feature lists presented during PPL/PL.
| Sprint Backlog | if used, how is it built | The sprint backlog is created from the prioritized project backlog. If needed tasks are split into smaller/achievable sub tasks.
| Kanban/ project board | if used, how is it built, and how are tasks allocated | Tasks involving alignment between multiple OpenHW contributors, as well as a subset of the larger tasks, are made visible via the following OpenHW github project boards: CV32E40X Design - https://github.com/openhwgroup/cv32e40x/projects/1 CV32E40S Design - https://github.com/openhwgroup/cv32e40s/projects/1 CV32E40X Testbench - https://github.com/openhwgroup/core-v-verif/projects/11 CV32E40S Testbench - https://github.com/openhwgroup/core-v-verif/projects/10 Core-V-Verif Common Infrastructure - https://github.com/openhwgroup/core-v-verif/projects/9 The other tasks remain internal to the Silicon Laboratories backlog (which contains other tasks related to these projects, but not related to OpenHW, as well).
| Sprint Planning method | how is each Sprint planned (e.g. Sprint planning meeting, decided by a TPL, etc.). How do OpenHW contributors get involved | On RTL design, new features are added and sanity tested per Sprint. Verification will likely work on these new features the subsequent Sprint. Steve and Arjan as product owners will make intial prioritization for the Sprint. Then the team has a look in a 2 hour Sprint planning meeting later in the day EU
| Daily Standup Meeting | if used, how is it organized | Yes every day, early in the day in Europe
| Sprint Review Meeting | if used, how is it organized | yes, quick demos of what has been done
| Sprint Retrospective Meeting | if used, how is it organized | maybe
| How are "done" tasks updated on Github |  | Designers continuously use PR. Jira ticke is closed after all related PR have been accepted. Arjan and Steve as PO decide what is "done". - that is a Jira level process
| How are these artifacts made available on Github |  | backlog is not proposed to be made available. Proposing to make external tasks tracked on github project
| Initial Gantt type schedule (like in Waterfall) | Optional to have an initial view of the project. Took approx 1 week of effort of leaders in cv32e40p | Will not be made (as it does not fit in the Agile way of working that is adopted).
Issue Management
| Overall approach for Github issues and labels |  | The Design side will follow the same approach for github issue and labels as used for CV32E40P. For the Verification side the existing model will be extended with the existence of specific labels per project (e.g. CV32E40X label and CV32E40S label).
| Task planning | template if available | Issues (including tasks, bugs) will be tracked via: https://github.com/openhwgroup/cv32e40x/issues https://github.com/openhwgroup/cv32e40s/issues https://github.com/openhwgroup/core-v-verif/issues (with appropriate labels) If tasks/bugs apply to both projects they will be filed in each project separately (and linked to each other). The github issue 'task' will not typically be used as the overview of the overall project tasks is performed via the Jira backlog.
| Bugs | template if available | See row above.
| Checklist review | template if available | The same checklists (possibly updated based on lessons learned) will be used as for the CV32E40P.
IP Issues
| Anticipated Contribution Questionnaire |  | The initial commits for the CV32E40X and CV32E40S have been performed and are identical to the CV32E40P RTL Freeze status. The next major Pull Request (identical for both projects) consists of about 170 commits and Eclipse has been asked to review the CQ for these PRs. After these already outstanding PRs no large PRs are currently planned as the goal is to perform commits at relatively low granularity (similar as during the CV32E40P project).
| Any deviation from project license approach from PL gate |  | No
| LIcense.md file | should exist | Exists (similar to CV32E40P; only IP name adapted)
Project Freeze Criteria
| Describe approach to checklists | likely copied from cv32e40p | The checklists used will be the same as those used for CV32E40P.
| Project Release version approach | likely copied from cv32e40p | Versioning approach will be the same as for CV32E40P.
| Project Release estimated schedule | taking into account Eclipse release process | Project Release will be at RTL Freeze time plus the time needed to complete the Eclipse release process (excluded on purpose as we do not control it).