## Slide 1: CV32E40Pv2 status
Pascal Gouédo
Yoann Pruvost

## Slide 2: Project
Project
  Design & Verification meeting
    Wednesday 14:00 CEST every 2 weeks(Ical)
  Dedicated technical meetings when needed
  Reporting to Cores TG
  Next: Make a mid-term schedule
Mattermost channels
  TWG : Cores : CV32E4*P
  TWG : Verification
Resources
  Pascal Gouédo
    Specification, Design, Verification
  Yoann Pruvost
    Design, Verification (core-v-verif & Formal)
  1 Sub-contractor
    Formal Verification (with OneSpin support)
OpenHW staff
  Mike
    Verification environment lead
    Technical support
  Davide
    Architecture & Design technical support

## Slide 3: Documentation
Specification
  PR #452: PULP instructions re-encoding table proposal
    Approved and merged
  PR #704: Documentation updated with PULP instructions re-encoding
    Reviewed, approved and merged in cv32e40p/dev
  Next : Hardware loops
    Add more details about constraints and behavior
    Analyze all HWLoops issues (#266, #583, #584, #598, #618)
    Specify behavior with respect to Interrupt and Debug

## Slide 4: Design
PR #707 (FPU integration in cv32e40p wrapper)
  Waiting for review and merge
Crossed FPU and OBI Data latencies uncovered:
  4 cases of GPR/CSR multiple/out-of-order write per instruction
  Multiple APU request generation per FPU instruction
   Started to describe each case in issues but need core-v-verif/cv32e40p hash to finalize (next slide)

## Slide 5: Verification
E40P core-v-verif environment
  New Tracer to cope with OBI Data latencies (cv32e40p PR #699)
  FPU move to cv32e40p + configurations management (core-v-verif PR #1274 depending on cv32e40p PR #707)
  Waiting for review and merge
  Environment fixes (core-v-verif PR #1273)  Merged
RVFI support in E40P core-v-verif environment
  Ci basic test passing with rvfi/rvvi env
  Waiting for Pascal’s PR to be merged before merging and issuing mine
  Once done, correct other CI tests
  https://github.com/YoannPruvost/cv32e40p/tree/dev_rvfi
  https://github.com/YoannPruvost/core-v-verif/tree/cv32e40p/dev_rvfi

## Slide 6: Formal Verification
CV32E40P
  RV32IMC
    No rule violation
  PULP instruction
    Started to make sail descriptions
FPU
  Use of unofficial cv32e40p_wrapper (Core + Fpnew) with OneSpin tools
  Starting to verify RV32F (all but DIV/SQRT)

## Slide 7: Tools
SW toolchain
  Embecosm business contract finalized (first step)

## Slide 8: Miscelaneous
Pull Request/Reviews/Merge
  Turn-around time is way too long
  Decreases a lot our productivity
    Especially when multiple inter-dependent PR
    And with our E40P/FPU formal verification sub-contractors