## Slide 1: CV32E40Pv2 status

## Slide 2: Project
Project
  Design & Verification meeting
    Wednesday 14:00 CEST every 2 weeks(Ical)
  Dedicated technical meetings when needed
  Reporting to Cores TG
  Next: Make a mid-term schedule
Mattermost channels
  TWG : Cores : CV32E4*P
  TWG : Verification
Resources
  Pascal Gouédo
    Specification, Design, Verification
  Yoann Pruvost
    Design, Verification (core-v-verif & Formal)
  Xavier Aubert
    Verification leader
  1 Sub-contractor
    Formal Verification (with OneSpin support)
OpenHW staff
  Mike
    Verification environment lead
    Technical support
  Davide
    Architecture & Design technical support

## Slide 3: Documentation
Specification
  Next
    Add a Revision History section
    Some analysis & cleanup
      privlv, uhartid,…
    Add MSTATUS.FS & MSTATUS.SD (once common agreement reached)
    Move from PULP_ZFINX to RISC-V Zfinx
    Hardware loops
      Add more details about constraints and behavior
      Analyze all HWLoops issues (#266, #583, #584, #598, #618)
      Specify behavior with respect to Interrupt and Debug

## Slide 4: Design
PR #716 (Move cv32e40p_fp_wrapper from bhv to rtl)
  Merge to be done
FPU test execution highlighted missing MSTATUS.FS & MSTATUS. SD
  Issue to be created & to be corrected (once common agreement reached)
Re-encoded PULP LD/ST and General ALU/Bit Manipulation/MAC RTL available for internal Formal verification
Crossed FPU and OBI Data latencies uncovered:
  4 cases of GPR/CSR multiple/out-of-order write per instruction
  Multiple APU request generation per FPU instruction
   Started to describe each case in issues

## Slide 5: Verification (1)
E40P core-v-verif environment
  All on-going PR merged (1273, 699, 1274)
  PR #1340 (step-and-compare update with F extension CSRs) created & merged
    Added F extension enable function in floating point test
    Showed missing MSTATUS.FS & SD
    Test ok with OBI stall disabled (no CSRs & full RF check)
    All FPU instructions need to be added to ISA Coverage
  XPULP re-encoded instruction
    Added ISS options to enable XPULP v2
    ISS requires privlv and uhartid non RISC-V CSRs
    To be removed from ISS or parametrized with PULP_SECURE?
    pulp_post_increment_load_store (re-encoded) execution shows tracer & step-and-compare are missing second GPR write functionality
  Google RISC-DV
    Started to add XPULP instructions

## Slide 6: Verification (2)
RVFI support in E40P core-v-verif environment
  Ci basic test passing with rvfi/rvvi env
  Waiting for Pascal’s PR to be merged before merging and issuing mine
  Once done, correct other CI tests
  https://github.com/YoannPruvost/cv32e40p/tree/dev_rvfi
  https://github.com/YoannPruvost/core-v-verif/tree/cv32e40p/dev_rvfi
Next
  Add Imperas Floating Point compliance tests in core-v-verif
  Switch E40Pv2 test-bench to RVVI/Imperas-DV framework once fully functional on E40X

## Slide 7: Formal Verification
CV32E40P
  RV32IMC
    No rule violation
  PULP instruction
    Sail descriptions finalized
    LD/ST rules verified at 70%
FPU
  Started to verify RV32F (all but DIV/SQRT)
  13 rules violations up to now due to
    F instructions decoding
    F instructions result impact on pipeline
    FFLAGS not correctly set

## Slide 8: Tools
SW toolchain
  Embecosm business contract finalized
  Toolchain development for re-encoded PULP instruction will start on September 1st, 2022
  Deliveries:
    October 1st
      Establish baseline RV32IMFCZcisr functionality, test and benchmarking environment
      Implement the PULP 8- and 16-bit SIMD extensions
    November 1st
      Implement the PULP bit manipulation extensions
      Implement the PULP 8- and 16-bit SIMD ext
    December 1st
      Implement Zfinx support
      Benchmarking
    Later on
      Hardware Loop support
      …

## Slide 9: Miscelaneous
Pull Request/Reviews/Merge
  Turn-around time is way too long
  Decreases a lot our productivity
    Especially when multiple inter-dependent PR
At least one Dolphin people should be able to be a “Committer” on core-v-verif and cv32e40p OpenHW github repos