## Sheet1
2021-03-22 | PA Gate Criteria | Detail
Top Level Items for PA Gate
| Requirements Specification | V1 agreed by TWG - see below for breakdown
| Project Plan | V1 agreed by TWG - see below for breakdown
Requirements Specification Item
| Document available on Github | V1 for review
| Document format | Markdown (RST, AsciiDocs, MD, etc.). All high level features should be identified (e.g. "security extensions"), with at least another level of detail down (e.g. "protection for CSR")
Project Plan Item
Availability & Format
| Plan document | V1 for review on Github
| Plan Document format | Plan could be any (editable) format
| Set of artifacts | What artifacts (schedule charts, project boards, etc.) will be used for project planning
| Plan artifacts available on Github | Initial version of project artifacts
Note how planning artifacts and tools will be available to OpenHW members
Note Any Changes from PL
Summary
| Components | Will be used to drive task list or backlog below
Members committed to participate
TPL/PM
Project Documents
Project Outputs
| Resources | Will lead into resource plan below
Summary of Requirements
Repository Structure
Distribution Model
Any other changes
Planning Approach
| Scope (e.g. design, design+verification, verification) | Are design and verification handled as a unified project or with separate projects?
Methodology (waterfall/agile/hybrid)
| Method for assigning tasks to persons | For Sprints or for waterfall assignment, do we consider design and verification as two different planning domains?
| Method for tracking tasks | How do OpenHW members see who is doing what?
| Planning tools disclosed (e.g. for schedule, project boards, Gantt charts) | Enough visibility on the tools to support collaborative multi-member development
Project Organization
Project structure or hierarchy if applicable
Project meeting cadence and timeslot
| Organization of interlocking projects | Different teams and plans for interlocked projects (e.g. cv32e40x and s)
| How design, verification, s/w, h/w teams interface | E.g., will there be separate or joint meetings for design and verification?
Human Resources
| Person(s) responsible for project planning | presumably the TPL/PM identified in PL gate
| Person(s) responsible for checklist verification | That is, this is the person/persons who need to sign off on the checklists
| Resource requirement breakdown for components/phases | To support multi-member development: Coarse grained view of project resource needs. For example, 2 design engineer months for design component x, 3 verification engineer months for verification component y
| Resource plan to meet requirements | Available people to allocate against resource needs
Flag resource issues or risks
Material Resources
Test boards, platforms or equipment
| Specify the set of EDA tools required for a designer or verification person to be involved in the project. | E.g. verilog simulator, reference model license, etc.
Specify the set of s/w tools needed for a resource to be involved
Risks and Dependencies
| Dependencies on external technology or efforts | E.g., external standard needs to be ratified
| Cross-project dependencies: related projects (e.g. s/w linked to a h/w project) | E.g., s/w or design task planned outside the project needs to be finished
| Cross-project dependencies: linked projects | E.g. dependence on a task linked to a separate Cores project.
| Risk-register | Risks, impacts, and mitigation plan
Schedule
| V1 of planned schedule | uploaded on Github
| Delineate coarse grained timeline | Project can organize the timeline according to the project nature, but schedule could be tied to major chunks of functionality. E.g. complete design for major component by end Q2 2022, etc.
| Milestones | Possibly tied to components, at least 2-3 would be ideal
Project Freeze planning date
Waterfall Specific Items
| Task breakdown | E.g. tasks could be viewed as 1 week duration. Detail at front end expected to be higher
| Gantt Chart, or another way of scheduling tasks and resource assignments | Detail at front end expected to be higher
Agile Specific Items
| Agile Methodology | Scrum, Kanban, other
| What element does the project backlog track | Features, tasks, or other
| Project backlog structure | How is it captured and maintained
| Initial project backlog | Nature of backlog items to be specified (features, tasks)
| Sprint Backlog | if used, how is it built
| Kanban/ project board | if used, how is it built, and how are tasks allocated
| Sprint Planning method | how is each Sprint planned (e.g. Sprint planning meeting, decided by a TPL, etc.). How do OpenHW contributors get involved
| Daily Standup Meeting | if used, how is it organized
| Sprint Review Meeting | if used, how is it organized
| Sprint Retrospective Meeting | if used, how is it organized
How are "done" tasks updated on Github
How are these artifacts made available on Github
| Initial Gantt type schedule (like in Waterfall) | Optional to have an initial view of the project. Took approx 1 week of effort of leaders in cv32e40p
Issue Management
Overall approach for Github issues and labels
| Task planning | template if available
| Bugs | template if available
| Checklist review | template if available
IP Issues
Anticipated Contribution Questionnaire
Any deviation from project license approach from PL gate
| LIcense.md file | should exist
Project Freeze Criteria
| Describe approach to checklists | likely as per cv32e40p
| Project Release version approach | likely as per cv32e40p
| Project Release estimated schedule | taking into account Eclipse release process