## Sheet1
CVE2 Project Plan | Owner/ Assigned | Proposed end date
Documentation
CVE2 User Manual | Joe | 2023-06-30
CVE2 DV Plan | Joe | 2023-06-30
Define/Review "RTL Freeze" completion metrics | Joe | 2023-06-30
Core Complex User Manual | Lee/Joe | 2023-06-30
Core Complex DV Plan | Lee/Joe | 2023-06-30
Verification
Integrate ImperasDV | Mike, Maarten | 2023-03-31
Updating verification environment | Maarten | 2023-03-31
Update Makefile for Xcelium | Maarten | 2023-03-31
Port existing Interrupt Agent from E40* | Mike, Lee | 2023-04-15
Implement and integrate interrupt tests | Lee | 2023-04-15
Port existing CSR environment from E40* | Maarten, Szymon | 2023-04-15
Implement and integrate CSR tests | Maarten, Szymon | 2023-04-15
Port existing PerfMon environment from E40* | Szymon | 2023-04-15
Implement and integrate PerfMon tests | Szymon | 2023-04-15
Create end of tests checks | Maarten | 2023-04-30
Port existing exception environment from E40* | Maarten, Szymon | 2023-04-30
Implement and integrate exception tests | Maarten, Szymon | 2023-04-30
Port existing debug environment from E40* | Maarten, Lee | 2023-05-15
Implement directed tests to exercise all debug features | Maarten, Lee | 2023-05-15
Code and integrate functional coverage of debug unit | Maarten, Lee | 2023-05-15
Tools |  | (done)
Review and update "Board Support Package"
Review of writing tests |  |  | Review of "Writing Tests for CORE-V-VERIF"
Develop and run a “sanity regression” using corev-dv random instruction generator | Maarten | 2023-03-31
RTL Design
Rename IBEX to CVE2 | Szymon | 2023-03-31
Remove unwanted code | Szymon | 2023-03-31
Design and integrate RVFI + RVVI | Maarten | 2023-03-31
Make needed OBI changes for compliance | Szymon | 2023-04-15
Create and integrate sleep unit | Szymon | 2023-04-15 | How does it relate to https://github.com/openhwgroup/cve2/pull/11
Design Completion (Wrap-up)
Review coverage holes from “sign-off” regression | All | 2023-06-15
Review any open issues | All | 2023-06-15
Port existing compliance environment from E40* | Maarten | 2023-06-15
Execute and debug to get 100% pass rate for all tests | All | 2023-06-15
Measure E20 performance metrics on select benchmarks, e.g., CoreMark, ULPBench, Dhrystone | All | 2023-06-15
Core Complex Design and Verification
RTL design of OBI2AHB | Lee | (done)
Integration of components (CLIC, debug) | Lee, Maarten | 2023-06-30
Core Complex TB verification | Lee, Maarten | 2023-08-31
Core Complex Design Completion | All | 2023-08-31
Project Freeze | All | 2023-08-31