## Slide 1: CV32E20 Plan Approved Review
Joe Circello (NXP), Lee Hoff (Intrinsix),
March 27, 2023

## Slide 2: CV32E20 Project Details
Project summary
  Ultra-low-end core cloned from Ibex (fka ETH-Zurich ZeroRISCY)
  Targeted at the low-end of RISC-V MCU roadmaps
    Any “compute constrained socket”
    Processor element in embedded SoC subsystems
Planning for an initial two-phase development
  Phase 1: RTL design of core starting from Ibex
    RV32IMC and RV32EMC ISAs
    OBI bus interfaces
    CV32E40P-like interrupt interface
    User and Machine privilege modes
  Phase 2: Create core-complex aka “coreplex”
    OBI to AHB-5 bridges (Intrinsix IP)
    Interrupt controller design INTC (OpenTitan from PULP)
    Debug design
Project resourcing
  Co-sponsored by NXP and Intrinsix
  NXP contributes architecture, RTL design and verification resources
  Intrinsix contributes bus gasket IP and verification resources
https://github.com/lowRISC/ibex/blob/master/README.md

## Slide 3: Project Details Continued
Core overview summary
  Optimized for minimum gate count and lowest power
Future (CV32E20v2) design enhancements under consideration
    Support for new compressed opcodes (“Zc”), possible inclusion of bit manipulation ISA
    Exploration of 2-pin CJTAG debug interface
    Exploration of ETH-Zurich’s “Tiny FPU”
    Low granularity Physical Memory Protection module (PMP)

## Slide 4: CV32E20: Status
Project gates
  PC gate passed on 6/2021
  PL gate passed on 2/2022
  PA gate up for vote on 3/2023
    Intended technical details are fairly well defined
    RTL design resources started at the beginning of August 2022
    Project completion now estimated as 8/31/2023
Project meetings
  Every Tuesday 9:00 EDT
Mattermost channel - TWG : Cores : CVE20
Github repository - github.com/openhwgroup/cve2

## Slide 5: CV32E20: Current Activities
Ongoing (weekly) discussions with multiple stakeholders
  OpenHW Design (Davide Schiavone)
  OpenHW Verification (Mike Thompson)
  Imperas (Simon Davidmann)
  Intrinsix + NXP CV32E20 teams
Recent discussions focused on…
  Core-V-Verif strategies
    Intent is to fully leverage existing Core-V-Verif strategy and methodologies (see next page)
  Imperas core configuration definition for reference model creation
Creation of core specifications underway
Initial design environment
  “Pipe cleaner” activities at both NXP + Intrinsix for GitHub repositories
  Initial set of diagnostics running at NXP

## Slide 6: CV32E20: Project Plan
Major Milestones: Due Date:
Documentation Complete 6/30/2023
Tools 3/31/2023
RTL Design 4/15/2023
Verification 5/15/2023
Design Completion 6/15/2023
Core Complex Design & Verification 8/31/2023
Project Freeze 8/31/2023